## Slide 1
Breakout Session Summary:
Review of Burmese Python Workshops and Next Steps
Rebekah Gibble (FWS) and Tylan Dean (ENP)

## Slide 2: Objective
Provide an overview of two recent python workshops: A structured decision making workshop focused on low-density management of pythons sponsored by USFWS and USGS (held June 2014) and a Science review workshop sponsored by ENP and USGS (held November 2013).
Discuss workshop findings, outcomes, and request feedback
Determine next steps for developing interagency management planning for Burmese pythons/large constrictors.

## Slide 3: Next Steps: Interagency Planning
Let’s Discuss…
  Who would be the key players in the process?
  What would the planning process entail?
  What is the appropriate framework for a plan?
  Are there points of contention?
  Are there outstanding gaps/needs?
  What is the status/role of the Task Force and the Python Executive Leadership Group?
Notes: Kristen Sommers (FWC), Tylan Dean (ENP), Rebekah Gibble (USFWS), Gintas

## Slide 4: We need one interagency plan
Decision:
  Plan for landscape scale
  Small group to develop (FWC, NPS, USFWS, Tribe)
  Include all constrictors
Action: Develop small team to :
  Develop Objective for management plan: Develop a comprehensive management plan for managing and controlling ecological impacts of large constrictors on a landscape scale
  Strawman framework for a plan (small team to develop to get buy-in from managers)
  Potentially use objective from executive meeting
Disseminate plan:
  Executive meeting
  DOI framework meeting
  ECISMA
Provide Carrie a project sheet for SAN framework
  Provide background and description of management plan development
Reconvene Executive python leadership –
  Related to SAN framework (basic principles apply)
  Needs and gaps discussion
Partners to engage at some point in the process
  Mgt Agencies: FWC, NPS, USFWS, SFWMD, Tribes, FDEP,
  State Park Service, Florida Forest Service, FPL, FDOT, DEP, ENP, Loxahatchee, Rookery Bay, Big Cypress, WCAs, Tribes
  Support: USGS, UF, USDA

## Slide 5
Action (Detection and/or removal) | Detection/ Control | Cost ($$/acre) | Available area (acres/area)
*Driving surveys | Medium/yes |  | 
*+Walking surveys | Medium/yes |  | 
*+Detection dogs | Medium/yes |  | 
*Capture/monitoring training (incl. authorized agents) | Medium/yes |  | 
Judas snakes | Medium/yes |  | 
*+Thermal refugia/traps | Uncertain/yes | See USDA | 
+Barriers (e.g., drift fence) | Uncertain/yes |  | 
+Marsh rabbit sentinels | High/yes |  | 
+Camera traps | Uncertain/no |  | 
+Tech enhanced wavelength | Uncertain/no |  | 
Public outreach | Uncertain/yes |  | 
*Determined to be priority for investment at DOI science meeting
+Additional research and development required
Notes: Not all inclusive – field discing, helicopter surveys

## Slide 6
Action (Detection and/or removal) | Detection/ Control | Cost ($$/acre) | Available area (acres/area)
*Driving surveys | Medium/yes |  | 
*+Walking surveys | Medium/yes |  | 
*+Detection dogs | Medium/yes |  | 
*Capture/monitoring training (incl. authorized agents) | Medium/yes |  | 
Judas snakes | Medium/yes |  | 
*+Thermal refugia/traps | Uncertain/yes | See USDA | 
+Barriers (e.g., drift fence) | Uncertain/yes |  | 
+Marsh rabbit sentinels | High/yes |  | 
+Camera traps | Uncertain/no |  | 
+Tech enhanced wavelength | Uncertain/no |  | 
Public outreach | Uncertain/yes |  | 
*Determined to be priority for investment at DOI science meeting
+Additional research and development required
Notes: Not all inclusive – field discing, helicopter surveys

## Slide 7
Plan that defines actions that can be implemented and be NEPA compliant
  For each group
Objective: What needs to be done to effectively address python issue